# Oracle C3 Agentic AI Platform - Migration Strategy

## 7.1 Migration Approach

### 7.1.1 Migration Strategy Selection

Selected Strategy: [Phased Migration / Big Bang / Hybrid]

| Strategy Option | Description | Pros | Cons | Decision |
| --- | --- | --- | --- | --- |
| Phased Migration | Migrate in waves over time | - Lower risk- Learning opportunity- Business continuity | - Longer timeline- Complex integration- Temporary dual operations | ✓ Selected |
| Big Bang | All systems at once | - Faster completion- No integration complexity- Clean cutover | - High risk- Extensive downtime- No rollback options | Not selected |
| Hybrid | Critical systems phased, others big bang | - Balanced risk- Optimized timeline- Flexibility | - Complex planning- Mixed approaches | Consider for specific apps |

### 7.1.2 Migration Principles

| Principle | Description | Implementation |
| --- | --- | --- |
| Business Continuity | Minimize disruption to operations | - Off-hours migrations- Parallel run periods- Rollback procedures |
| Risk Mitigation | Reduce migration risks | - Pilot migrations- Comprehensive testing- Incremental approach |
| Data Integrity | Zero data loss | - Data validation- Reconciliation- Backup verification |
| Performance Validation | Meet or exceed current performance | - Baseline metrics- Load testing- Performance tuning |
| Security First | Maintain security posture | - Security testing- Compliance validation- Access reviews |

### 7.1.3 Migration Patterns by Workload Type

| Workload Type | Pattern | Tools | Timeline |
| --- | --- | --- | --- |
| Lift & Shift | Direct VM migration | OCI + C3 Migration tools | 1-2 weeks per app |
| Re-platform | Migrate to C3 AI services | C3 Studio + migration scripts | 2-4 weeks per app |
| Refactor | C3 AI containerization | C3 Studio, C3 Type System | 4-8 weeks per app |
| Rebuild | C3 AI-native redesign | C3 Studio development | 8-12 weeks per app |
| Replace | C3 AI SaaS adoption | C3 Platform tools | 4-6 weeks per app |

## 7.2 Migration Phases

### 7.2.1 Phase Overview

┌─────────────────┐     ┌─────────────────┐     ┌─────────────────┐
│   Phase 0       │     │   Phase 1       │     │   Phase 2       │
│  Foundation     │────▶│  Non-Production │────▶│   Production    │
│  (4 weeks)      │     │  (6 weeks)      │     │  Wave 1         │
└─────────────────┘     └─────────────────┘     │  (4 weeks)      │
                                                 └────────┬────────┘
                                                          │
┌─────────────────┐     ┌─────────────────┐     ┌────────▼────────┐
│   Phase 5       │     │   Phase 4       │     │   Phase 3       │
│  Optimization   │◄────│  Decommission   │◄────│   Production    │
│  (Ongoing)      │     │  (4 weeks)      │     │   Wave 2        │
└─────────────────┘     └─────────────────┘     │  (4 weeks)      │
                                                 └─────────────────┘

### 7.2.2 Phase 0: Foundation (Weeks 1-4)

#### Objectives

- Establish OCI + C3 AI environment

- Set up connectivity

- Implement security baseline

- Create C3 AI migration infrastructure

#### Activities

| Week | Activities | Deliverables | Success Criteria |
| --- | --- | --- | --- |
| 1 | - Provision OCI + C3 tenancy- Create C3 AI compartments- Set up C3 IAM | - C3 Platform active- C3 IAM policies | - C3 access working- Policies tested |
| 2 | - Configure networking- Establish VPN/FastConnect- Set up DNS | - Network design- Connectivity | - On-prem connected- DNS resolving |
| 3 | - Deploy security tools- Configure monitoring- Set up backup | - Security baseline- Monitoring dashboards | - Security scanning- Alerts working |
| 4 | - Create C3 migration tools- Test C3 procedures- Train team on C3 Studio | - C3 migration runbooks- Test results | - C3 tools validated- Team C3-ready |

### 7.2.3 Phase 1: Non-Production Migration (Weeks 5-10)

#### Objectives

- Migrate development to C3 environment

- Migrate test environment

- Validate C3 AI migration procedures

- Performance baseline

#### Migration Schedule

| Environment | Applications | Week | Method | Downtime |
| --- | --- | --- | --- | --- |
| Development | App1, App2, App3 | 5 | Lift & shift to C3 | 8 hours |
| Development | Database Dev | 6 | Data Pump | 4 hours |
| Test | App1, App2 | 7 | Re-platform to C3 Studio | 8 hours |
| Test | App3, C3 Analytics DB Test | 8 | Re-platform to C3 | 8 hours |
| UAT | All applications | 9 | Clone from Test | 4 hours |
| Integration Test | End-to-end | 10 | N/A | N/A |

### 7.2.4 Phase 2: Production Wave 1 (Weeks 11-14)

#### Objectives

- Migrate low-risk production workloads

- Validate production procedures

- Build confidence

#### Wave 1 Applications

| Application | Criticality | Users | Migration Date | Method | Downtime | Rollback |
| --- | --- | --- | --- | --- | --- | --- |
| HR Portal | Low | 500 | Week 11 | Lift & shift | 4 hours | VM snapshot |
| Internal Wiki | Low | 1000 | Week 11 | Re-platform | 2 hours | Database backup |
| Dev Tools | Medium | 200 | Week 12 | Containerize | 1 hour | Previous version |
| Reporting App | Medium | 300 | Week 13 | Re-platform | 4 hours | Database restore |

### 7.2.5 Phase 3: Production Wave 2 (Weeks 15-18)

#### Objectives

- Migrate business-critical applications

- Complete data migration

- Full production cutover

#### Wave 2 Applications

| Application | Criticality | Users | Migration Date | Method | Downtime | Special Considerations |
| --- | --- | --- | --- | --- | --- | --- |
| ERP System | High | 5000 | Week 15-16 | Re-platform | 8 hours | - Weekend migration- All hands support- Executive communication |
| Customer Portal | High | 50000 | Week 17 | Blue-green | 0 | - Gradual traffic shift- 24hr monitoring |
| Core Database | High | All | Week 18 | GoldenGate | <5 min | - Real-time replication- Extensive testing |

### 7.2.6 Phase 4: Decommission (Weeks 19-22)

#### Objectives

- Validate all migrations successful

- Decommission old infrastructure

- Cost optimization

#### Decommission Schedule

| Component | Validation Period | Decommission Date | Data Retention |
| --- | --- | --- | --- |
| Dev/Test Servers | 2 weeks | Week 19 | Snapshots for 90 days |
| Production Servers | 4 weeks | Week 21 | Snapshots for 1 year |
| Network Equipment | 4 weeks | Week 22 | Config backup permanent |
| Licenses | Immediate | Week 19 | N/A |

### 7.2.7 Phase 5: Optimization (Ongoing)

#### Objectives

- Right-size resources

- Implement auto-scaling

- Cost optimization

- Performance tuning

## 7.3 Data Migration Plan

### 7.3.1 Data Migration Strategy by Type

| Data Type | Volume | Method | C3 AI Tool | Duration | Validation |
| --- | --- | --- | --- | --- | --- |
| Databases |  |  |  |  |  |
| OLTP Database | 500GB | Online replication | GoldenGate + C3 connectors | 48 hours initial + CDC | Row counts, checksums |
| C3 Analytics Warehouse | 5TB | Offline export | Data Pump + C3 loaders | 5 days | C3 sample queries |
| NoSQL Data | 1TB | API migration | C3 Type System scripts | 3 days | Document count |
| File Systems |  |  |  |  |  |
| Shared Drives | 2TB | Rsync over VPN | Rsync | 7 days | File count, size |
| Media Files | 10TB | Physical transfer | Data Transfer Appliance | 14 days | Checksums |
| Object Storage |  |  |  |  |  |
| Backups | 20TB | Cloud-to-cloud | Rclone | 10 days | Object count |
| Archives | 50TB | Offline transfer | Data Transfer Appliance | 21 days | Manifest validation |

### 7.3.2 Database Migration Deep Dive

#### Oracle Database Migration

Source DB                    C3 AI Migration Process            C3 Target DB
─────────                   ──────────────────                ─────────
┌─────────────┐            ┌─────────────────┐              ┌─────────────┐
│  On-Prem    │    Initial │   GoldenGate    │   Real-time  │ C3 AI on OCI│
│  Oracle DB  │◄──────────▶│   Replication   │◄────────────▶│ C3 Analytics│
│  (500GB)    │    Load    │                 │     CDC      │   Database  │
└─────────────┘            └────────┬────────┘              └─────────────┘
                                    │
                           ┌────────▼────────┐
                           │   Validation    │
                           │  - Row counts   │
                           │  - Checksums    │
                           │  - App testing │
                           └─────────────────┘

#### Migration Steps

- Initial Setup (Day 1)

  - Configure GoldenGate

  - Create target schema

  - Set up network connectivity

- Initial Load (Day 2-3)

  - Export source data

  - Load to target

  - Verify data integrity

- CDC Sync (Day 4-7)

  - Start change data capture

  - Monitor lag time

  - Performance tuning

- Validation (Day 7-8)

  - Run validation queries

  - Application testing

  - Performance comparison

- Cutover (Day 9)

  - Stop applications

  - Final sync

  - Switch connections

  - Validate operations

### 7.3.3 Data Validation Framework

| Validation Type | Method | Tools | Acceptance Criteria |
| --- | --- | --- | --- |
| Completeness | Row counts | SQL queries | 100% match |
| Integrity | Checksums | MD5/SHA256 | Checksum match |
| Consistency | Referential integrity | SQL constraints | No violations |
| Accuracy | Sample comparison | Custom scripts | 100% sample match |
| Performance | Query execution | AWR reports | ≤ baseline time |

## 7.4 Application Migration

### 7.4.1 Application Migration Patterns

| Pattern | When to Use | Process | Example Apps |
| --- | --- | --- | --- |
| Rehost | - Minimal changes needed- Time constraints- Stable applications | 1. Create VM in OCI2. Install C3 runtime3. Copy application4. Update C3 configs | Legacy apps, COTS |
| Replatform | - Benefit from C3 services- Reduce operations | 1. Provision C3 service2. Modify C3 config3. Deploy to C3 Studio4. Update C3 connections | AI apps, analytics |
| Refactor | - C3 AI modernization needed- AI scalability required | 1. Containerize with C32. Create C3 manifests3. Deploy to C3 Platform4. Implement C3 CI/CD | AI microservices |
| Rebuild | - Major AI architecture change- C3 AI-native benefits | 1. Redesign with C3 Studio2. Develop C3 AI-native3. Implement C3 DevOps4. Progressive deployment | New AI development |

### 7.4.2 Application Migration Checklist

| Task | Owner | Dev | Test | Prod | Notes |
| --- | --- | --- | --- | --- | --- |
| Pre-Migration |  |  |  |  |  |
| Document current state | App Team | ✓ | ✓ | ✓ | Architecture, configs, dependencies |
| Identify dependencies | App Team | ✓ | ✓ | ✓ | Databases, services, integrations |
| Create migration runbook | Migration Team | ✓ | ✓ | ✓ | Step-by-step procedures |
| Set up C3 target environment | C3 Platform Team | ✓ | ✓ | ✓ | C3 compute, network, storage |
| Migration |  |  |  |  |  |
| Deploy to C3 Platform | C3 App Team | ✓ | ✓ | ⧖ | Follow C3 runbook |
| Update C3 configurations | C3 App Team | ✓ | ✓ | ⧖ | C3 connections, endpoints |
| Migrate data | DBA Team | ✓ | ✓ | ⧖ | If app-specific data |
| Configure monitoring | Ops Team | ✓ | ✓ | ⧖ | Alerts, dashboards |
| Post-Migration |  |  |  |  |  |
| Functional testing | QA Team | ✓ | ✓ | ⧖ | Full regression |
| Performance testing | Perf Team | ✓ | ✓ | ⧖ | Load, stress tests |
| Security validation | Security Team | ✓ | ✓ | ⧖ | Scans, penetration tests |
| Go-live approval | Management | N/A | N/A | ⧖ | Sign-off required |

## 7.5 Cutover Planning

### 7.5.1 Cutover Strategy by Application

| Application | Strategy | Cutover Window | Rollback Time | Decision Point |
| --- | --- | --- | --- | --- |
| HR Portal | Hard cutover | 2 hours | 30 minutes | 1.5 hours |
| Customer Portal | Blue-green deployment | 0 downtime | Immediate | N/A |
| ERP System | Parallel run | 48 hours | 4 hours | 24 hours |
| Core Database | Active-passive flip | 15 minutes | 15 minutes | 10 minutes |

### 7.5.2 Detailed Cutover Plan - ERP System

| Time | Activity | Owner | Duration | Success Criteria | Rollback |
| --- | --- | --- | --- | --- | --- |
| Friday 10:00 PM |  |  |  |  |  |
| T-2:00 | Communication sent | PM | 5 min | All users notified | N/A |
| T-1:00 | Final data backup | DBA | 60 min | Backup verified | N/A |
| Saturday 12:00 AM |  |  |  |  |  |
| T+0:00 | Freeze transactions | App Team | 5 min | No new transactions | N/A |
| T+0:05 | Stop applications | App Team | 10 min | All services stopped | Restart services |
| T+0:15 | Final data sync | DBA | 120 min | Data synchronized | Restore backup |
| T+2:15 | Update DNS/configs | Network | 15 min | Connections updated | Revert configs |
| T+2:30 | Start applications | App Team | 15 min | Services running | Stop and rollback |
| T+2:45 | Validation testing | QA Team | 60 min | Core functions work | Execute rollback |
| T+3:45 | Go/No-go decision | Management | 15 min | Approval to proceed | Execute rollback |
| T+4:00 | Monitor and stabilize | Ops Team | 240 min | System stable | Still possible |

### 7.5.3 Communication Plan

| Audience | When | Message | Channel | Owner |
| --- | --- | --- | --- | --- |
| All Users | T-1 week | Migration announcement | Email, Portal | PM |
| Business Leaders | T-3 days | Detailed schedule | Meeting | PM |
| All Users | T-1 day | Reminder and instructions | Email, SMS | PM |
| IT Staff | T-2 hours | Final checklist | Slack, Call | Tech Lead |
| All Users | T+0 | System unavailable | Portal, Email | PM |
| Executives | T+2 hours | Progress update | Call | PM |
| All Users | T+4 hours | System available | Email, SMS | PM |
| All Staff | T+1 day | Success summary | Email | PM |

### 7.5.4 Rollback Procedures

| Scenario | Detection | Decision Time | Rollback Steps | Duration |
| --- | --- | --- | --- | --- |
| Data corruption | Validation queries fail | Immediate | 1. Stop apps2. Restore backup3. Restart old system | 2 hours |
| Performance issues | Response time >5x baseline | 1 hour | 1. Redirect traffic2. Investigate3. Fix or rollback | 30 minutes |
| Integration failures | External systems can’t connect | 30 minutes | 1. Update endpoints2. Restart services3. Revert if needed | 1 hour |
| Critical bugs | Core functions fail | Immediate | 1. Assess impact2. Hotfix or rollback3. Communicate | Variable |

## 7.6 Migration Risk Management

### 7.6.1 Migration-Specific Risks

| Risk | Probability | Impact | Mitigation | Contingency |
| --- | --- | --- | --- | --- |
| Extended downtime | Medium | High | - Detailed planning- Practice runs- Parallel systems | - Rollback procedures- Executive communication |
| Data loss | Low | Critical | - Multiple backups- Validation scripts- Incremental sync | - Point-in-time recovery- Manual reconciliation |
| Performance degradation | Medium | High | - Load testing- Capacity planning- Tuning | - Scale resources- Code optimization |
| Integration failures | Medium | Medium | - Early testing- Stub services- Monitoring | - Fallback endpoints- Manual processes |
| User adoption issues | High | Medium | - Training plan- Documentation- Support team | - Extended support- Quick reference guides |

### 7.6.2 Migration Success Factors

| Factor | Requirement | How to Ensure |
| --- | --- | --- |
| Executive Support | Active sponsorship | Regular updates, escalation path |
| User Communication | Clear, timely, accurate | Communication plan, multiple channels |
| Technical Expertise | Skilled resources | Training, vendor support, consultants |
| Testing Coverage | Comprehensive validation | Test plans, automation, user acceptance |
| Rollback Capability | Quick recovery option | Documented procedures, practice runs |