# Oracle C3 Agentic AI Platform Implementation Plan

Platform: Oracle C3 Agentic AI Platform
Implementation Model: C3 AI Platform Deployment Methodology
Reference: C3 AI Implementation Best Practices

## 8.1 C3 AI Platform Project Scope

### 8.1.1 C3 AI Implementation In Scope

| Category | C3 AI Items | Details |
| --- | --- | --- |
| C3 AI Platform |  |  |
| C3 Platform Deployment | Oracle C3 AI Platform setup | Full platform installation on OCI with HA configuration |
| C3 Studio IDE Setup | Development environment | Multi-user C3 Studio with version control and collaboration |
| Ex Machina Deployment | Visualization framework | Dashboard and analytics UI deployment |
| C3 AI Applications |  |  |
| AI Model Development | Predictive models, digital workers | C3 Studio development and Ex Machina deployment |
| Enterprise Integration | SAP, Salesforce, Oracle connectors | C3 connector configuration and data integration |
| Data Integration |  |  |
| Canonical Data Model | C3 Type System implementation | Unified data schema with C3 AI optimization |
| Real-time Data Feeds | Streaming data ingestion | C3 data loaders and stream processing |
| AI Services |  |  |
| Model Training Pipeline | ML model lifecycle management | Automated training, validation, and deployment |
| Generative AI Integration | C3 GenAI services | LLM integration for intelligent automation |

### 8.1.2 Out of Scope

| Category | Items | Rationale |
| --- | --- | --- |
| Applications |  |  |
| Custom ML Model Development | Will use C3 AI pre-built models and templates |  |
| Third-party AI Tools | C3 AI Platform provides comprehensive AI capabilities |  |
| Infrastructure |  |  |
| On-premises AI Hardware | C3 AI Platform cloud-native deployment only |  |
| Legacy Analytics Systems | Will be replaced by C3 AI platform capabilities |  |
| Data |  |  |
| Historical Data >5 years | Phase 2 implementation after core platform |  |
| Training |  |  |
| End-user Training | Separate training project after platform deployment |  |
| Change Management | Organizational change management separate initiative |  |

### 8.1.3 Assumptions and Prerequisites

| Assumption | Impact | Validation Required |
| --- | --- | --- |
| OCI tenancy available | Project can start on schedule | Procurement team confirmation |
| Network connectivity established | Migration can proceed | Network team delivery |
| Business stakeholder availability | Requirements can be validated | Resource commitment |
| Current system documentation exists | Planning can be completed | Documentation audit |

## 8.2 Work Breakdown Structure

### 8.2.1 Phase Overview

Project Lifecycle (24 weeks)
│
├── Phase 1: Foundation (Weeks 1-6)
│   ├── Project Initiation
│   ├── Architecture Design
│   ├── OCI Environment Setup
│   └── Tool Configuration
│
├── Phase 2: Pilot Migration (Weeks 7-12)
│   ├── Non-Production Migration
│   ├── Process Validation
│   ├── Performance Testing
│   └── Security Validation
│
├── Phase 3: Production Migration (Weeks 13-20)
│   ├── Wave 1: Low Risk Apps
│   ├── Wave 2: Business Critical Apps
│   ├── Data Migration
│   └── Integration Testing
│
└── Phase 4: Stabilization (Weeks 21-24)
    ├── Performance Optimization
    ├── Documentation
    ├── Knowledge Transfer
    └── Project Closure

### 8.2.2 Detailed Work Packages

#### Phase 1: Foundation (Weeks 1-6)

| Work Package | Duration | Deliverables | Dependencies |
| --- | --- | --- | --- |
| WP1.1: Project Initiation | 2 weeks |  |  |
| Stakeholder alignment | 1 week | - Kickoff meeting- RACI matrix- Communication plan | Team assignments |
| Requirements validation | 1 week | - Requirements sign-off- Scope confirmation | Business availability |
| WP1.2: Architecture Design | 3 weeks |  |  |
| Logical architecture | 1 week | - Architecture diagrams- Component specifications | Requirements complete |
| Physical architecture | 1 week | - Infrastructure design- Sizing calculations | Performance requirements |
| Security design | 1 week | - Security architecture- Control specifications | Compliance requirements |
| WP1.3: OCI Environment Setup | 2 weeks |  |  |
| Foundation services | 1 week | - Tenancy setup- IAM configuration- Networking | OCI access |
| Security baseline | 1 week | - Security groups- Policies- Monitoring | Foundation complete |
| WP1.4: Tool Configuration | 1 week |  |  |
| Migration tools | 1 week | - Tool installation- Configuration- Testing | Environment ready |

#### Phase 2: Pilot Migration (Weeks 7-12)

| Work Package | Duration | Deliverables | Dependencies |
| --- | --- | --- | --- |
| WP2.1: Non-Production Migration | 3 weeks |  |  |
| Development environment | 1 week | - Dev apps migrated- Connectivity tested | Foundation ready |
| Test environment | 2 weeks | - Test apps migrated- End-to-end testing | Dev migration |
| WP2.2: Process Validation | 1 week |  |  |
| Migration procedures | 1 week | - Runbooks validated- Process refined | Pilot complete |
| WP2.3: Performance Testing | 1 week |  |  |
| Load testing | 1 week | - Performance baseline- Optimization plan | Apps available |
| WP2.4: Security Validation | 1 week |  |  |
| Security testing | 1 week | - Vulnerability scan- Penetration test | Security tools ready |

#### Phase 3: Production Migration (Weeks 13-20)

| Work Package | Duration | Deliverables | Dependencies |
| --- | --- | --- | --- |
| WP3.1: Wave 1 Migration | 2 weeks |  |  |
| Low-risk applications | 2 weeks | - Apps migrated- User acceptance | Pilot validated |
| WP3.2: Wave 2 Migration | 4 weeks |  |  |
| Business-critical apps | 4 weeks | - Apps migrated- Performance validated | Wave 1 complete |
| WP3.3: Data Migration | 3 weeks |  |  |
| Database migration | 2 weeks | - Data migrated- Validation complete | Apps ready |
| File migration | 1 week | - Files migrated- Access validated | Storage ready |
| WP3.4: Integration Testing | 1 week |  |  |
| End-to-end testing | 1 week | - Integration validated- Performance confirmed | All systems migrated |

#### Phase 4: Stabilization (Weeks 21-24)

| Work Package | Duration | Deliverables | Dependencies |
| --- | --- | --- | --- |
| WP4.1: Optimization | 2 weeks |  |  |
| Performance tuning | 2 weeks | - Optimized performance- Cost optimization | Migration complete |
| WP4.2: Documentation | 1 week |  |  |
| Operational docs | 1 week | - Run books- Architecture docs | Systems stable |
| WP4.3: Knowledge Transfer | 1 week |  |  |
| Team training | 1 week | - Training delivered- Skills validated | Documentation ready |
| WP4.4: Project Closure | 1 week |  |  |
| Project closure | 1 week | - Lessons learned- Final report | All deliverables complete |

## 8.3 Timeline and Milestones

### 8.3.1 Master Timeline

| Phase | Start Date | End Date | Duration | Key Milestones |
| --- | --- | --- | --- | --- |
| Phase 1: Foundation | [WEEK_1] | [WEEK_6] | 6 weeks | - Project kickoff- Architecture approved- OCI environment ready |
| Phase 2: Pilot | [WEEK_7] | [WEEK_12] | 6 weeks | - Non-prod migrated- Processes validated- Go/no-go decision |
| Phase 3: Production | [WEEK_13] | [WEEK_20] | 8 weeks | - Wave 1 complete- Wave 2 complete- All data migrated |
| Phase 4: Stabilization | [WEEK_21] | [WEEK_24] | 4 weeks | - System optimized- Team trained- Project closed |

### 8.3.2 Critical Path Analysis

| Critical Path Activities | Duration | Slack | Risk Level |
| --- | --- | --- | --- |
| Architecture design → OCI setup → Non-prod migration | 6 weeks | 0 days | High |
| Non-prod validation → Go/no-go → Prod migration | 2 weeks | 1 week | Medium |
| Data migration → Integration testing → Go-live | 4 weeks | 0 days | High |

### 8.3.3 Key Decision Points

| Decision Point | Date | Decision Criteria | Decision Maker | Impact if Delayed |
| --- | --- | --- | --- | --- |
| Architecture Approval | Week 4 | - Design meets requirements- Security review passed- Cost approved | Architecture Board | 2-week delay |
| Go/No-Go for Production | Week 12 | - Pilot successful- Performance acceptable- Business approval | Steering Committee | Project restart |
| Wave 2 Approval | Week 15 | - Wave 1 stable- Lessons learned applied | IT Director | 1-week delay |
| Project Acceptance | Week 23 | - All success criteria met- User acceptance achieved | Project Sponsor | Extended warranty |

## 8.4 Resource Plan

### 8.4.1 Team Structure

Project Organization
│
├── Executive Sponsor
│   └── Steering Committee
│
├── Project Manager
│   ├── Project Coordinator
│   └── Change Manager
│
├── Technical Stream
│   ├── Solution Architect (Lead)
│   ├── Infrastructure Architect
│   ├── Security Architect
│   ├── Database Architect
│   └── Network Engineer
│
├── Migration Stream
│   ├── Migration Lead
│   ├── Application Migration Engineers (3)
│   ├── Data Migration Specialist
│   └── Testing Coordinator
│
├── Operations Stream
│   ├── Operations Lead
│   ├── System Administrators (2)
│   ├── Database Administrator
│   └── Monitoring Specialist
│
└── Business Stream
    ├── Business Analyst
    ├── Training Coordinator
    └── User Acceptance Lead

### 8.4.2 Resource Requirements by Phase

| Role | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total Effort |
| --- | --- | --- | --- | --- | --- |
| Core Team |  |  |  |  |  |
| Project Manager | 1.0 FTE | 1.0 FTE | 1.0 FTE | 1.0 FTE | 24 weeks |
| Solution Architect | 1.0 FTE | 0.8 FTE | 0.6 FTE | 0.4 FTE | 17 weeks |
| Migration Lead | 0.5 FTE | 1.0 FTE | 1.0 FTE | 0.5 FTE | 18 weeks |
| Technical Team |  |  |  |  |  |
| Infrastructure Engineer | 1.0 FTE | 0.8 FTE | 1.0 FTE | 0.6 FTE | 20 weeks |
| Database Specialist | 0.5 FTE | 0.8 FTE | 1.0 FTE | 0.4 FTE | 16 weeks |
| Security Engineer | 1.0 FTE | 0.6 FTE | 0.4 FTE | 0.2 FTE | 13 weeks |
| Network Engineer | 0.8 FTE | 0.4 FTE | 0.6 FTE | 0.2 FTE | 12 weeks |
| Migration Team |  |  |  |  |  |
| App Migration Engineers | 1.5 FTE | 3.0 FTE | 3.0 FTE | 1.0 FTE | 52 weeks |
| Testing Coordinator | 0.5 FTE | 1.0 FTE | 1.0 FTE | 0.5 FTE | 18 weeks |
| Business Team |  |  |  |  |  |
| Business Analyst | 1.0 FTE | 0.5 FTE | 0.8 FTE | 0.4 FTE | 16 weeks |
| Change Manager | 0.5 FTE | 0.8 FTE | 1.0 FTE | 1.0 FTE | 19 weeks |

### 8.4.3 Skills Matrix

| Role | Required Skills | Experience Level | Availability | Training Needed |
| --- | --- | --- | --- | --- |
| Solution Architect | OCI, Enterprise Architecture | Senior (5+ years) | Full-time | OCI certification |
| Migration Lead | Migration tools, Project mgmt | Senior (5+ years) | Full-time | OCI migration tools |
| Infrastructure Engineer | OCI Compute, Networking | Mid-level (3+ years) | Full-time | OCI networking |
| Database Specialist | Oracle, Migration tools | Senior (5+ years) | 80% available | Autonomous DB |
| Security Engineer | Cloud security, Compliance | Senior (5+ years) | 60% available | OCI security |

### 8.4.4 External Resources

| Resource Type | Provider | Duration | Cost | Purpose |
| --- | --- | --- | --- | --- |
| Oracle Consulting | Oracle | 8 weeks | $[Amount] | Architecture review, best practices |
| Migration Specialists | [Vendor] | 12 weeks | $[Amount] | Migration execution support |
| Security Consultants | [Vendor] | 4 weeks | $[Amount] | Security assessment, compliance |
| Training Services | [Provider] | 2 weeks | $[Amount] | Team upskilling |

## 8.5 RACI Matrix

### 8.5.1 Key Activities RACI

| Activity | Sponsor | PM | Architect | Eng Team | Business | Ops Team |
| --- | --- | --- | --- | --- | --- | --- |
| Planning |  |  |  |  |  |  |
| Project charter | A | R | C | I | C | I |
| Architecture design | A | C | R | C | C | C |
| Resource allocation | A | R | C | I | I | I |
| Execution |  |  |  |  |  |  |
| Environment setup | C | A | R | R | I | C |
| Application migration | I | A | C | R | C | C |
| Data migration | I | A | C | R | I | R |
| Testing | C | A | C | C | R | C |
| Go-Live |  |  |  |  |  |  |
| Go/no-go decision | R | A | C | C | C | C |
| Cutover execution | A | A | C | R | I | R |
| Issue resolution | C | A | C | R | I | R |
| Closure |  |  |  |  |  |  |
| User acceptance | C | A | I | I | R | I |
| Documentation | I | A | C | R | C | R |
| Knowledge transfer | C | A | C | C | I | R |

Legend: R = Responsible, A = Accountable, C = Consulted, I = Informed

### 8.5.2 Decision Authority Matrix

| Decision Type | Primary | Backup | Escalation |
| --- | --- | --- | --- |
| Technical decisions | Solution Architect | Technical Lead | CTO |
| Scope changes | Project Manager | Project Sponsor | Steering Committee |
| Go/no-go decisions | Project Sponsor | IT Director | Executive Sponsor |
| Resource assignments | Project Manager | Resource Manager | IT Director |
| Budget approval | Project Sponsor | Finance Director | CFO |

## 8.6 Risk Management

### 8.6.1 Implementation Risks

| Risk | Probability | Impact | Mitigation | Contingency |
| --- | --- | --- | --- | --- |
| Technical Risks |  |  |  |  |
| Migration tool failures | Medium | High | - Pilot testing- Backup procedures- Vendor support | Manual migration procedures |
| Performance degradation | Medium | High | - Load testing- Capacity planning- Performance monitoring | Scale resources, optimize code |
| Data corruption | Low | Critical | - Validation scripts- Backup verification- Incremental migration | Point-in-time recovery |
| Resource Risks |  |  |  |  |
| Key resource unavailable | Medium | Medium | - Cross-training- Documentation- Backup resources | External consultants |
| Skills gap | High | Medium | - Training program- Mentoring- External support | Additional consulting |
| Business Risks |  |  |  |  |
| User resistance | Medium | Medium | - Change management- Training- Communication | Extended support period |
| Business disruption | Low | High | - Phased approach- Rollback plans- Weekend migrations | Emergency procedures |

### 8.6.2 Success Factors

| Factor | Requirements | How to Ensure |
| --- | --- | --- |
| Executive Support | Active sponsorship | Regular updates, clear escalation |
| Technical Expertise | Skilled team | Training, mentoring, external support |
| Business Engagement | User involvement | Regular communication, training |
| Quality Processes | Rigorous testing | Test plans, automation, validation |
| Change Management | Smooth transition | Communication, training, support |